## Activities
Experimental activities | 2014
| ID nr. | Experimental activities - cropping | Plot size | Plot size | Expected Yield | Estm. dry matter | Expected harvest |  | Harvest time |  | Storage time | Sample size | Stored as | Stored at | Planned analyses |  |  | Comments
|  |  | m*m | ha | tons TS/ha | % | kg TS | kg | Start | End | Mdr. | kg | frozen/dry |  | A | B | C
AU Crop rotation large plots - Foulum
| AU-F 1 | 1 Tritricale + Italian ryegrass/red clover
|  | Harvest tritricale whole crop | 12*20 | 0.024 | 7.5 | 92 | 180 | 195.6522 | 2014-07-10 | 2014-07-17 | 10 | 1.5 | f | AU | 3
|  | Harvest grass clower | 12*20 | 0.024 | 8.1 | 91 | 194.4 | 213.6264 | 2014-10-01 | 2014-10-15 | 8 | 1.5 | f | AU | 3
| AU-F 2 | 2 Maize + winter rye
|  | Harvest maize | 12*20 | 0.024 | 2.5 | 25 | 60 | 240 | 2014-10-01 | 2014-11-01 | 8 | 1.5 | f | AU | 3
|  | Harvest winter rye | 12*20 | 0.024 | 11.2 | 55 | 268.8 | 488.7273 | 2015-04-01 | 2015-05-15 | 12 | 1.5 | f | AU | 3
| AU-F 3 | 3 Fodder beet
Harvest tops
|  | Harvest roots | 12*20 | 0.024 | 26.6 | 25 | 638.4 | 2553.6 | 2014-11-01 | 2014-11-21 | 12 | 1.5 | f | AU | 3
| AU-F 4 | 4 Hemp
|  | Harvest hemp | 12*20 | 0.024 | 12.7 | 65 | 304.8 | 468.9231 | 2014-09-01 | 2014-09-15 | 10 | 1.5 | f | AU | 3
| AU-F 5 | 5 Grain crop rotation
|  | Harvest kernels | 12*20 | 0.024 | 9.4 | 90 | 225.6 | 250.6667 | 2014-08-01 | 2014-08-20 | 10 | 5 | d | AU | 3 |  |  | Winter barley in 2014
|  | Harvest straw | 12*20 | 0.024 | 4.5 | 87 | 108 | 124.1379 | 2014-08-01 | 2014-08-20 | 10 | 5 | d | AU | 3
AU Permanent crop large plots - Foulum
| AU-F 6 | 6 Miscanthus giganteus
|  | Harvest | 12*20 | 0.024 | 3.5 | 50 | 84 | 168 | 2014-10-01 | 2014-10-21 | 8 | 1.5 | f | AU | 3
| AU-F 7 | 7 Miscanthus sacchariflorus
|  | Harvest | 12*20 | 0.024 | 0.4 | 50 | 9.6 | 19.2 | 2014-10-01 | 2014-10-21 | 8 | 1.5 | f | AU | 3
| AU-F 8 | 8 Festulolium (tall fescue x perennial ryegrass)
|  | Harvest 1 | 12*20 | 0.024 | 11.5 | 50 | 276 | 552 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 2 | 12*20 | 0.024 | 7.5 | 50 | 180 | 360 | 2014-08-01 | 2014-08-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 3 | 12*20 | 0.024 | 4 | 50 | 96 | 192 | 2014-10-01 | 2014-10-31 | 8 | 1.5 | f | AU | 3
| AU-F 9 | 9 Continuous winter wheat - straw removal
|  | Harvest | 12*20 | 0.024 | 12.1 | 80 | 290.4 | 363 | 2014-08-01 | 2014-08-30 | 8 | 5 | d | AU | 3
| AU-F 10 | 10 Continuous maize
|  | Harvest | 12*20 | 0.024 | 15.7 | 75 | 376.8 | 502.4 | 2014-10-01 | 2014-10-30 | 8 | 1.5 | f | AU | 3
| AU-F 11 | 11 Bare soil - mechanical treatment | 12*20 | 0.024 | 0
| AU-F 12 | 12 Bare soil- no mechanical treatment | 12*20 | 0.024 | 0
| AU-F 13 | 13 Willow
|  | Harvest | 12*20 | 0.024 |  |  | 0 | #DIV/0! |  |  |  | 5 | d | AU |  |  |  | harvest vinter 2015
AU Permanent crops small plots - Foulum
| AU-F 14 | 14 Reed canary grass
|  | Harvest 1 | 3*12 m | 0.0036 | 8 | 28 | 28.8 | 102.8571 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 2 | 3*12 m | 0.0036 | 4.5 | 28 | 16.2 | 57.8571 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 3 | 3*12 m | 0.0036 | 3.3 | 28 | 11.88 | 42.4286 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 4 | 3*12 m | 0.0036 | 2 | 28 | 7.2 | 25.7143 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
| AU-F 15 | 15 Tall fescue
|  | Harvest 1 | 3*12 m | 0.0036 | 8.5 | 28 | 30.6 | 109.2857 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 2 | 3*12 m | 0.0036 | 5.5 | 28 | 19.8 | 70.7143 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 3 | 3*12 m | 0.0036 | 3.3 | 28 | 11.88 | 42.4286 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 4 | 3*12 m | 0.0036 | 2 | 28 | 7.2 | 25.7143 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
| AU-F 16 | 16 Cocksfoot grass
|  | Harvest 1 | 3*12 m | 0.0036 | 6.5 | 28 | 23.4 | 83.5714 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 2 | 3*12 m | 0.0036 | 4.1 | 28 | 14.76 | 52.7143 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 3 | 3*12 m | 0.0036 | 3 | 28 | 10.8 | 38.5714 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 4 | 3*12 m | 0.0036 | 2 | 28 | 7.2 | 25.7143 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
| AU-F 17 | 17 Grass mixture with alfa alfa
|  | Harvest 1 | 3*12 m | 0.0036 | 5 | 28 | 18 | 64.2857 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvets 2 | 3*12 m | 0.0036 | 3 | 28 | 10.8 | 38.5714 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 3 | 3*12 m | 0.0036 | 2.7 | 28 | 9.72 | 34.7143 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 4 | 3*12 m | 0.0036 | 2 | 28 | 7.2 | 25.7143 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 4
| AU-F 18 | 18 Grass mixture DLF trifolium
|  | Harvest 1 | 3*12 m | 0.0036 | 4 | 28 | 14.4 | 51.4286 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 2 | 3*12 m | 0.0036 | 3.1 | 28 | 11.16 | 39.8571 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | harvest 3 | 3*12 m | 0.0036 | 1 | 28 | 3.6 | 12.8571 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 4 | 3*12 m | 0.0036 | 0.5 | 28 | 1.8 | 6.4286 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 4
| AU-F | Total | [12 empty] | 103 | 0 | 0
AU Crop rotation large plots - Jyndevad
| AU-J 1 | 1 Winter rye + winter rape
|  | Harvest winter rye whole crop | 12*20 | 0.024 | 7 | 92 | 168 | 182.6087 | 2014-07-10 | 2014-07-17 | 10 | 1.5 | f | AU | 3
|  | Harvest rape whole crop | 12*20 | 0.024 | 5 | 87 | 120 | 137.931 | 2014-07-10 | 2014-07-17 | 10 | 1.5 | f | AU | 3
| AU-J 2 | 2 Hemp + winter rye
|  | Harvest hemp | 12*20 | 0.024 | 12.2 | 65 | 292.8 | 450.4615 | 2014-09-01 | 2014-09-15 | 10 | 1.5 | f | AU | 3
|  | Harvest winter rye whole crop | 12*21 | 0.024 | 11.2 | 55 | 268.8 | 488.7273 | 2014-09-01 | 2014-09-15 | 10 | 1.5 | f | AU | 3
| AU-J 3 | 3 Maize + winter rye
|  | Harvest maize | 12*20 | 0.024 | 10.7 | 55 | 256.8 | 466.9091 | 2014-10-01 | 2014-10-15 | 12 | 1.5 | f | AU | 3
AU Permanent crop large plots - Jyndevad
| AU-J 4 | 4 Cocksfoot grass (Donata)
|  | Harvest 1 | 3*12 m | 0.0036 | 6.5 | 28 | 23.4 | 83.5714 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 2 | 3*12 m | 0.0036 | 4.1 | 28 | 14.76 | 52.7143 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 3 | 3*12 m | 0.0036 | 3 | 28 | 10.8 | 38.5714 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 4 | 3*12 m | 0.0036 | 2 | 28 | 7.2 | 25.7143 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU
| AU-J 5 | 5 Miscanthus sinensis
|  | Harvest | 12*20 | 0.024 | 0.4 | 50 | 9.6 | 19.2 | 2014-10-01 | 2014-10-21 | 8 | 1.5 | f | AU | 3
| AU-J 6 | 6 Continuous maize
|  | Harvest | 12*20 | 0.024 | 15.7 | 75 | 376.8 | 502.4 | 2014-10-01 | 2014-10-30 | 8 | 1.5 | f | AU | 3
AU Permanent crops small plots - Jyndevad
| AU-J 7 | 7 Reed canary grass
|  | Harvest 1 | 3*12 m | 0.0036 | 8 | 28 | 28.8 | 102.8571 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 2 | 3*12 m | 0.0036 | 4.5 | 28 | 16.2 | 57.8571 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 3 | 3*12 m | 0.0036 | 3.3 | 28 | 11.88 | 42.4286 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 4 | 3*12 m | 0.0036 | 2 | 28 | 7.2 | 25.7143 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
| AU-J 8 | 8 Tall fescue
|  | Harvest 1 | 3*12 m | 0.0036 | 8.5 | 28 | 30.6 | 109.2857 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 2 | 3*12 m | 0.0036 | 5.5 | 28 | 19.8 | 70.7143 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 3 | 3*12 m | 0.0036 | 3.3 | 28 | 11.88 | 42.4286 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 4 | 3*12 m | 0.0036 | 2 | 28 | 7.2 | 25.7143 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
| AU-J 9 | 9 Cocksfoot grass (Amba)
|  | Harvest 1 | 3*12 m | 0.0036 | 6.5 | 28 | 23.4 | 83.5714 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 2 | 3*12 m | 0.0036 | 4.1 | 28 | 14.76 | 52.7143 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 3 | 3*12 m | 0.0036 | 3 | 28 | 10.8 | 38.5714 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 4 | 3*12 m | 0.0036 | 1.5 | 28 | 5.4 | 19.2857 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
| AU-J 10 | 17 Grass mixture wit alfa alfa
|  | Harvest 1 | 3*12 m | 0.0036 | 5 | 28 | 18 | 64.2857 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvets 2 | 3*12 m | 0.0036 | 3 | 28 | 10.8 | 38.5714 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 3 | 3*12 m | 0.0036 | 2.7 | 28 | 9.72 | 34.7143 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 4 | 3*12 m | 0.0036 | 1.7 | 28 | 6.12 | 21.8571 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
| AU-J 11 | 18 Grass mixture 2 DLF trifolium
|  | Harvest 1 | 3*12 m | 0.0036 | 4 | 28 | 14.4 | 51.4286 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 2 | 3*12 m | 0.0036 | 3.1 | 28 | 11.16 | 39.8571 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | harvest 3 | 3*12 m | 0.0036 | 1 | 28 | 3.6 | 12.8571 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
|  | Harvest 4 | 3*12 m | 0.0036 | 0.5 | 28 | 1.8 | 6.4286 | 2014-05-01 | 2014-05-30 | 8 | 1.5 | f | AU | 3
| AU-J | Total | [12 empty] | 90 | 0 | 0
Agrotech
Straw + catch crop yield
| AT1 | Cerals + catch crop 1 (barley, ryegrass)
|  | Harvest 1 | 3*12 m | 0.0036 | 6 | 65 | 21.6 | 33.2308 | 2014-06-25 | 2014-07-01 | 8 | 5 | f | AT | 3
|  | Harvest 2 | 3*12 m | 0.0036 | 6.5 | 70 | 23.4 | 33.4286 | 2014-07-02 | 2014-07-14 | 8 | 5 | f | AT | 3
|  | Harvest 3 | 3*12 m | 0.0036 | 7 | 80 | 25.2 | 31.5 | 2014-07-15 | 2014-07-30 | 8 | 5 | f | AT | 3
|  | Harvest 4 (mature) | 3*12 m | 0.0036 | 7.5 | 87 | 27 | 31.0345 | 2014-08-01 | 2014-08-30 | 8 | 5 | f | AT | 3
|  | Harvest 5 | 3*12 m | 0.0036 | 4.5 | 25 | 16.2 | 64.8 | 2014-10-01 | 2014-10-30 | 8 | 5 | f | AT | 3
| AT2 | Cerals + catch crop 2 (barley, ryegrass)
|  | Harvest 1 | 3*12 m | 0.0036 | 6 | 65 | 21.6 | 33.2308 | 2014-06-25 | 2014-07-01 | 8 | 5 | f | AT | 3
|  | Harvest 2 | 3*12 m | 0.0036 | 6.5 | 70 | 23.4 | 33.4286 | 2014-07-02 | 2014-07-14 | 8 | 5 | f | AT | 3
|  | Harvest 3 | 3*12 m | 0.0036 | 7 | 80 | 25.2 | 31.5 | 2014-07-15 | 2014-07-30 | 8 | 5 | f | AT | 3
|  | Harvest 4 (mature) | 3*12 m | 0.0036 | 7.5 | 87 | 27 | 31.0345 | 2014-08-01 | 2014-08-30 | 8 | 5 | f | AT | 3
|  | Harvest 5 | 3*12 m | 0.0036 | 4.5 | 25 | 16.2 | 64.8 | 2014-10-01 | 2014-10-30 | 8 | 5 | f | AT | 3
| AT3 | Perennial grass fertilization 1 (Tall fescue)
|  | Harvest 1 | 3*12 m | 0.0036 | 10 | 25 | 36 | 144 | 2014-08-01 | 2014-08-30 | 8 | 5 | f | KU | 3
|  | Harvest 2 | 3*12 m | 0.0036 | 12 | 25 | 43.2 | 172.8 | 2014-08-01 | 2014-08-30 | 8 | 5 | f | KU | 3
|  | Harvest 4 | 3*12 m | 0.0036 | 14 | 25 | 50.4 | 201.6 | 2014-08-01 | 2014-08-30 | 8 | 5 | f | KU | 3
|  | Harvest 3 | 3*12 m | 0.0036 | 16 | 25 | 57.6 | 230.4 | 2014-08-01 | 2014-08-30 | 8 | 5 | f | KU | 3
| AT4 | Perennial grass fertilization 2 (Tall fescue)
|  | Harvest 1 | 3*12 m | 0.0036 | 10 | 25 | 36 | 144 | 2014-08-01 | 2014-08-30 | 8 | 5 | f | KU | 3
|  | Harvest 2 | 3*12 m | 0.0036 | 12 | 25 | 43.2 | 172.8 | 2014-08-01 | 2014-08-30 | 8 | 5 | f | KU | 3
|  | Harvest 3 | 3*12 m | 0.0036 | 14 | 25 | 50.4 | 201.6 | 2014-08-01 | 2014-08-30 | 8 | 5 | f | KU | 3
|  | Harvest 4 | 3*12 m | 0.0036 | 16 | 25 | 57.6 | 230.4 | 2014-08-01 | 2014-08-30 | 8 | 5 | f | KU | 3
Storage - lab scale
Straw + catch crop
Straw + beet leaves
Grain from cereals
Beet and leaves -feed for catle
| AT | Total | [12 empty] | 54 | 0 | 0
Sejet
| SE1 | Wheat type aa
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE2 | Wheat type ab
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE3 | Wheat type ac
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE4 | Wheat type ad
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE5 | Wheat type ae
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE6 | Wheat type af
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE7 | Wheat type ag
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE8 | Wheat type ah
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE9 | Wheat type ai
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE10 | Wheat type aj
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| S11 | Wheat type ak
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE12 | Wheat type al
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE13 | Wheat type am
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE14 | Wheat type an
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE15 | Wheat type ao
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE16 | Wheat type ap
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE17 | Wheat type aq
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE18 | Wheat type ar
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE19 | Wheat type as
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE20 | Wheat type at
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE21 | Wheat type au
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE22 | Wheat type av
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE23 | Wheat type ax
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE24 | Wheat type ay
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE25 | Wheat type az
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE26 | Wheat type ba
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE27 | Wheat type bb
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE28 | Wheat type bc
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE29 | Wheat type bd
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE30 | Wheat type be
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE31 | Wheat type bf
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE32 | Wheat type bg
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE33 | Wheat type bh
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE34 | Wheat type bi
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE35 | Wheat type bj
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| SE36 | Wheat type bk
|  | Harvest kernels | 3*5 | 0.0015 | 7.2 | 84 | 10.8 | 12.8571 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
|  | Havest straw | 3*5 | 0.0015 | 3.6 | 86 | 5.4 | 6.2791 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | SE | 3
| Sejet | Total | [12 empty] | 216 | 0 | 0
KU Crop rotation plots
| KU1 | Wheat - Ambition
|  | Harvest kernels | 3*5 | 0.0015 | 7.1 | 85 | 10.65 | 12.5294 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
|  | Havest straw | 3*5 | 0.0015 | 3.5 | 87 | 5.25 | 6.0345 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
| KU2 | Wheat - Audi
|  | Harvest kernels | 3*5 | 0.0015 | 7.1 | 85 | 10.65 | 12.5294 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
|  | Havest straw | 3*5 | 0.0015 | 3.5 | 87 | 5.25 | 6.0345 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
| KU3 | Wheat - Genius
|  | Harvest kernels | 3*5 | 0.0015 | 7.1 | 85 | 10.65 | 12.5294 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
|  | Havest straw | 3*5 | 0.0015 | 3.5 | 87 | 5.25 | 6.0345 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
| KU4 | Wheat - Gedser
|  | Harvest kernels | 3*5 | 0.0015 | 7.1 | 85 | 10.65 | 12.5294 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
|  | Havest straw | 3*5 | 0.0015 | 3.5 | 87 | 5.25 | 6.0345 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
| KU5 | Wheat - Hereford
|  | Harvest kernels | 3*5 | 0.0015 | 7.1 | 85 | 10.65 | 12.5294 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
|  | Havest straw | 3*5 | 0.0015 | 3.5 | 87 | 5.25 | 6.0345 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
| KU6 | Wheat - Hybery
|  | Harvest kernels | 3*5 | 0.0015 | 7.1 | 85 | 10.65 | 12.5294 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
|  | Havest straw | 3*5 | 0.0015 | 3.5 | 87 | 5.25 | 6.0345 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
| KU7 | Wheat - Evolution
|  | Harvest kernels | 3*5 | 0.0015 | 7.1 | 85 | 10.65 | 12.5294 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
|  | Havest straw | 3*5 | 0.0015 | 3.5 | 87 | 5.25 | 6.0345 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
| KU8 | Wheat - JB Asano
|  | Harvest kernels | 3*5 | 0.0015 | 7.1 | 85 | 10.65 | 12.5294 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
|  | Havest straw | 3*5 | 0.0015 | 3.5 | 87 | 5.25 | 6.0345 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
| KU9 | Wheat - Jensen
|  | Harvest kernels | 3*5 | 0.0015 | 7.1 | 85 | 10.65 | 12.5294 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
|  | Havest straw | 3*5 | 0.0015 | 3.5 | 87 | 5.25 | 6.0345 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
| KU10 | Wheat - Mariboss
|  | Harvest kernels | 3*5 | 0.0015 | 7.1 | 85 | 10.65 | 12.5294 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
|  | Havest straw | 3*5 | 0.0015 | 3.5 | 87 | 5.25 | 6.0345 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
| KU11 | Wheat - Nakskov
|  | Harvest kernels | 3*5 | 0.0015 | 7.1 | 85 | 10.65 | 12.5294 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
|  | Havest straw | 3*5 | 0.0015 | 3.5 | 87 | 5.25 | 6.0345 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
| KU12 | Wheat - SJ8544003
|  | Harvest kernels | 3*5 | 0.0015 | 7.1 | 85 | 10.65 | 12.5294 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
|  | Havest straw | 3*5 | 0.0015 | 3.5 | 87 | 5.25 | 6.0345 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
| KU13 | Tritricale - SJ070909-38
|  | Harvest kernels | 3*5 | 0.0015 | 7.1 | 85 | 10.65 | 12.5294 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
|  | Havest straw | 3*5 | 0.0015 | 3.5 | 87 | 5.25 | 6.0345 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
| KU14 | Wheat - Pierrot
|  | Harvest kernels | 3*5 | 0.0015 | 7.1 | 85 | 10.65 | 12.5294 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
|  | Havest straw | 3*5 | 0.0015 | 3.5 | 87 | 5.25 | 6.0345 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
| KU15 | Wheat - Tuareg
|  | Harvest kernels | 3*5 | 0.0015 | 7.1 | 85 | 10.65 | 12.5294 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
|  | Havest straw | 3*5 | 0.0015 | 3.5 | 87 | 5.25 | 6.0345 | 2014-08-01 | 2014-08-31 | 12 | 5 | d | KU | 3
| KU | Total | [12 empty] | 90 | 0 | 0

## Expla
Explanations
Abbreviations
| AU-F | Aarhus Univeristy - Foulum
| AU-J | Aarhus University - Jyndevad
| AT | Agrotech
| KU | Copenhaven University
| SE | Sejet

## Analy
Analyses |  | wait for input from Søren
| Type | Parameters |  | Unit | Method
| A | Water content | TS | %
|  | Ash Content | TSG | %
|  | Mineral N | N | mg/kg TS
|  | Mineral P | P | mg/kg TS
|  | Mineral P | K | mg/kg TS
|  | Total protein |  | mg/kg TS
B
| C | Special analyses